GlucoLink A2 – Demo video outline

Owner: Minha Kim (F-5) · For the Sunday 11 Oct 22:00 meeting · Draft v0.1, 10 October 2026

Purpose of this document: agree who narrates each section, what is on screen, and how long it runs, so that each owner can record their clip on Mon 12 – Tue 13 Oct. Nothing is recorded before the clean 00→10 run in glucolink_a2_test (Zhihao + Minha, Sun 11 Oct 18:00); the scripts are frozen after that run and every clip is recorded from that state.

# 1. Fixed points

- Order (from the tutor): (1) where the data comes from → (2) how it is extracted and loaded → (3) the objects in each layer RAW / CLEANSED / CURATED → (4) testing → (5) reports and dashboards.

- Length: about 8–10 minutes. Target 9:00; hard ceiling 10:00.

- Database shown: glucolink_a2_test after the Sunday clean run, frozen commit [fill in after the run]. Every CloudBeaver screen shows the database name in the header.

- Deadlines: clips to Minha by Mon 12 Oct 21:00 (late clips Tue 13 Oct 12:00 at the latest); assembled video uploaded to YouTube (unlisted) and link posted in Teams and in report section 3.5.6 by Tue 13 Oct 21:00.

# 2. Section outline

| # | Section | Narrator | What is on screen | Time |
| --- | --- | --- | --- | --- |
| 0 | Opening – problem and architecture | Xiaolong (A) | Title card (team, student IDs). docs/architecture_v2.png: three source systems → RAW → CLEANSED → CURATED → reporting views → Excel. One sentence per use case. | 0:45 |
| 1 | Where the data comes from | Quang (C), with Zhihao (B) for 02b | GitHub: sql/01_src_tables.sql and 02_src_data.sql headers. CloudBeaver: src_gp, src_lab, src_pharm table list; counts 3/18/28, 2/17, 3/3/13/68; one row each of gp_patient, lab_patient, pharmacy_patient for Thomas Smith to show the three different identifiers and name formats. Zhihao: 02b loads the 36 FHIR JSON messages and 34 deliveries (one JSON example on screen). | 1:30 |
| 2 | How it is extracted and loaded | Quang (C) | sql/03_raw_extract.sql: one block that copies a source table into raw.* with the four provenance columns (_source_system, _source_table, _pipeline_run_id, _loaded_at). Run order 00→10 as a table (from report 3.3). CloudBeaver: audit.pipeline_run showing 03_raw_extract SUCCESS, 225 rows read and loaded. | 1:00 |
| 3a | RAW layer objects | Quang (C) | CloudBeaver: the 11 raw tables; one query raw vs src count = equal (test L05). | 0:30 |
| 3b | CLEANSED layer objects | Yutong (D) | sql/04 and 05 headers. cleansed.patient_record 48 rows; the Card D four-row check (GP-0001 / PATH0001 / PH-1001 / PH-1014); dq_status VALID 33 / DUPLICATE 1 / REJECTED_UNIT 1 / FUTURE_DATE 1; patient_master 17; patient_source_link LINKED 46 / REVIEW 1 (PATH0006) / UNMATCHED 1 (PH-1012); precision 1.000, recall 28/29. | 1:15 |
| 3c | CURATED layer objects | Shuo (E) | docs/star_schema_v1.png (or logical model). sql/06 and 07 headers. dim_patient 17, dim_date 730; fact_encounter 28, fact_lab_result 32, fact_dispense 65; one join from fact_lab_result to dim_patient and dim_date to show surrogate keys. | 1:00 |
| 4 | Testing | Minha (F) | tests/test_plan_v1.xlsx: 43 planned tests in 8 categories. sql/09_tests.sql: one INSERT (e.g. U202) to show expected vs actual text. Run 09 live or show the result: audit.test_result summary 46 tests / 46 passed / 0 failed; failures query returns 0 rows. One slide on the six hand-checked patients (tests/A_hand_checks.xlsx) agreeing with the views. Mention the second full run (R02) proving repeatability. | 1:30 |
| 5 | Reports and dashboards | Minha (F); Yutong and Shuo each say one sentence on their views (optional) | sql/10_demo_queries.sql: the four view listings in CloudBeaver (UC1 8, UC2 11, UC3 16, UC4 2). Excel F_Reporting_Dashboard_v1.xlsx: Control and Checks sheets (parameters, counts PASS), then the four charts; for each, one sentence on what a care coordinator does with it (e.g. Thomas Smith HIGH_NO_REVIEW; Mei Chen PDC 0.333; Thomas Smith and Zoe Clark rising despite adherence; Olivia Brown result not returned). | 1:45 |
| 6 | Closing | Xiaolong (A) | Results in numbers (precision 1.000, recall 28/29, 8/11/16/2 rows, all tests passed), limitations (synthetic data, single as-of date, PDC simplification), GitHub repository and report pointer. | 0:30 |
|  | Total |  |  | 9:45 |

Table 1: Section outline (times are targets; trim 3b and 5 first if the total runs over 10:00)

# 3. Narration prompts per section

Each owner writes 4–6 sentences for their part. The prompts below are the points the tutor's order asks for; keep the numbers exactly as in the final run.

## 0 Opening (Xiaolong)

- GlucoLink has GP, pathology and pharmacy records with no shared patient ID; the prototype integrates them in PostgreSQL and answers four care-coordination questions.

- Walk the architecture diagram left to right in one breath; name the four use cases.

## 1 Where the data comes from (Quang, Zhihao)

- Three source schemas in one database stand in for three systems; 18 designed test patients with known answers.

- Show the same person in three formats (Medicare "2123 45670 1" vs "2123456701/1" vs "2123456701").

- Zhihao: the lab sends FHIR-style JSON messages; 02b loads 36 messages and 34 deliveries.

## 2 Extract and load (Quang)

- 03 copies every source table unchanged into RAW and adds provenance columns; each run writes one audit.pipeline_run row.

- Scripts run in number order, each reads only the layer before it (decision D8), and a second run does not duplicate fixture rows.

## 3 Layer objects (Quang, Yutong, Shuo)

- RAW: 11 tables, counts equal to source.

- CLEANSED: standardisation (names, ISO dates, Medicare to 10 digits, % to mmol/mol), data-quality statuses, and identity resolution with rules GP / R1 / R2; REVIEW and UNMATCHED records are never merged.

- CURATED: star schema with conformed dimensions and three fact tables; only VALID events of LINKED patients.

## 4 Testing (Minha)

- Plan first, then SQL: every test has an expected value from the business rules and the designed patients.

- 09_tests.sql writes audit.test_result; passed = (actual = expected); summary shows 0 failed.

- Independent hand checks by Xiaolong on six patients agree with the views.

- The clean run in an empty database and the second run prove the scripts are complete and repeatable.

## 5 Reports and dashboards (Minha)

- Views are the single source of truth; Excel only charts the exported rows after the Checks sheet passes.

- One sentence per dashboard on the action a care coordinator takes.

## 6 Closing (Xiaolong)

- Numbers, limitations, where to find the code (GitHub private; Appendix 6.5).

# 4. Recording and assembly

## 4.1 Before anyone records (Sun 11 Oct)

- 18:00 – clean 00→10 run in empty glucolink_a2_test with Zhihao (B-6 / F-5); 09 summary 46/46/0; screenshot 2026-10-11_BF_full_rerun.png; post "scripts frozen, commit <hash>" in Teams.

- Re-export UC1–UC4 from glucolink_a2_test into F_Reporting_Dashboard_v1.xlsx; Checks all PASS; charts final.

- 22:00 meeting – confirm this outline, narrators and times; everyone writes their 4–6 sentences by Mon 12 Oct 12:00.

## 4.2 How each owner records (Mon 12 – Tue 13 Oct)

- Tool: any screen recorder with microphone (macOS QuickTime "New Screen Recording", Windows Xbox Game Bar Win+G, or OBS). 1920×1080 or the full display, system audio off, microphone on. Alternatively record in a Teams call with Minha and let Minha capture the screen.

- Setup: CloudBeaver connected to glucolink_a2_test (database name visible), SQL editor font zoomed to 125–150 %, result grid visible without horizontal scroll, no credentials, no personal tabs. Queries pre-written in a scratch tab; run with Ctrl+Enter during the clip.

- Delivery: one clip per section, MP4 (or MOV), named A2_video_<section>_<name>.mp4 (e.g. A2_video_3b_Yutong.mp4), uploaded to the Teams channel Files folder "Video clips" by Mon 12 Oct 21:00. If a clip must be redone, keep the same name with _v2.

- Length discipline: record against the target time in Table 1; a clip may run 15 s over, not more. Minha trims pauses but does not cut content.

## 4.3 Assembly and upload (Minha, Tue 13 Oct)

- Join clips in order 0→6 (iMovie / CapCut / DaVinci Resolve); add section title cards (2 s each) with the tutor's five headings; normalise audio volume.

- Opening title card: GlucoLink A2 – Group 2 – names and student IDs – 16 October 2026. Closing card: GitHub repository name and "report section 3.5".

- Export 1080p MP4; watch once end to end; check total length ≤ 10:00 and that every CloudBeaver frame shows the database name.

- Upload to YouTube as Unlisted; title "GlucoLink A2 – Group 2 – Demo"; description with section timestamps.

- Post the link in Teams and paste it into report section 3.5.6; by Tue 13 Oct 21:00.

# 5. Minha's task list

| When | Task | Status |
| --- | --- | --- |
| Sat 11 Oct | Circulate this outline in Teams; ask each owner to confirm their section and time. | to do |
| Sun 11 Oct 18:00 | Clean 00→10 run with Zhihao; freeze commit; 09 summary screenshot. | to do |
| Sun 11 Oct evening | Re-export views, finish the four dashboards, Checks PASS. | to do |
| Sun 11 Oct 22:00 | Present the outline at the meeting; fix narrators and times; agree the recording tool. | to do |
| Mon 12 Oct | Record sections 4 and 5; be available on Teams to co-record with owners who prefer a call; collect clips by 21:00. | to do |
| Tue 13 Oct | Assemble, review, export, upload (unlisted), post link in Teams and report by 21:00. | to do |

Table 2: Owner checklist